## Roadmap
Actuarial Large Language Model Project Roadmap
Created By | Business Unit | Business Unit Sponsor
Pavan Singh (E1002902) | Advanced Analytics (Sanlam Retail Affluent Cluster) | Shabbeer Omar
1. Project Vision
The delivery of a powerful and customised AI assistant that can leverage the company's proprietary knowledge and domain expertise, which will enable more accurate, context-aware, and tailored responses, ultimately enhancing efficiency, productivity, and decision-making processes within the Actuarial, whilst also ensuring the confidentiality and privacy.
2. Project Strategy
The final delivery will be exectue through a multifaceted approach, encompassing exploration of existing LLM solutions, upskilling the project team within this domain, leveraging internal expertise from Sanlam Group Technology (SGT), and iterative development within a secure sandbox environment. Initially, a baseline or generic (not augmented with additional information) LLM model will be developed and released on the Azure platform which will ensure that users have a safe (data privacy ensured) space to query and recieve responses. Subsequently, we will iteratively enhance this generic LLM by integrating Sanlam-specific knowledge sources and proprietary data, which will enable the AI assistant to deliver Sanlam context specific responses.
3. Project Stakeholders
Person | Role(s) | Team / Unit ¦ Role
Niel van Rensburg | Executive Sponsor | SRA Actuarial ¦ Exec Head SRA Actuarial
Shabbeer Omar | Project Sponsor | Advanced Analytics ¦ Head of Advanced Analytics / Chief Analytics Officer
Luyanda Dhlamini | Project Advisor | Advanced Analytics ¦ Snr Data Scientist
Pavan Singh | Project Lead | Advanced Analytics ¦ Assoc Data Scientist
Kalind Ramnarayan | Actuarial (SME) Support | Advanced Analytics ¦ Actuarial Analytics Lead
Craig Strachan | Architect Support | SGT ¦ BI Solution Architect
4. Project Deliveries
Product Delivery Name | 1. Explore & Upskill LLM Knowledge
Delivery Description | Exploring and and upskilling in Large Language Models (LLMs) to familiarise the project team (and stakeholders) with their capabilities and applications in the context of actuarial tasks. This includes conducting research, exploring open-source applications, and hands-on experiments to understand LLM architectures, methodologies, and best practices. Additionally, contact shall be established with SGT for understanding the workings of their LLM implementations. The aim is to equip the team with the knowledge and skills necessary to leverage LLMs effectively in subsequent project phases.
What will be delivered | 1) Project team will deliver a comprehensive documentation covering the findings from the exploration and upskilling activities, which includes: working of large language models, open-source experimentations and SGT implementations 2) Presentation, which encapsulates the learnings of LLMs, SGT implementations and open-source solution viability
For Who | SRA Actuarial Senior Management Committee
Delivery Lead | Pavan Singh
By When | 2 Months Duration; Deadline: 1 April 2024
Project Delivery Features
1
2
3
Product Delivery Name | 2. Securing Azure AI Sandbox
Delivery Description | Focus on securing a sandbox environment from the SGT team on Azure platform to facilitate safe experimentation and development with Azure AI services. Additionally, the team focus on upskilling and working with Azure services, to facillitate the development of various architectures in subsequent project phases.
What will be delivered | 1) An actuarial sandbox environment, allowing for development of architectures in subsequent project phases 2) Documentation and guidelines interacting and using Azure services for development
For Who | SRA Actuarial Senior Management Committee
Delivery Lead | Pavan Singh
By When | 1.5 Months Duration; Deadline: 15 May 2024
Project Delivery Features
1
2
3
Product Delivery Name | 3. Generic LLM Development on Azure AI Sandbox
Delivery Description | Development and integration of Azure AI template to create an interface enabling querying of a generic large language model (LLM) within the Azure AI sandbox environment. The team will leverage Azure AI services and tools to build this capability. The development process will largely consist of integration of various architectures under Azure services.
What | 1) An interface configured to enable querying of a generic Large Language Model (LLM) within the Azure AI sandbox environment 2) User training materials providing guidance on utilising the LLM querying interface, querying procedures, and interpreting query results within the secure sandbox environment 3) Testing reports demonstrating the functionality and reliability of the LLM querying interface within the Azure AI sandbox environment
For Who | SRA Actuarial Senior Management Committee
Delivery Lead | Pavan Singh
By When | 1 Months Duration; Deadline: 15 June 2024
Project Delivery Features
1
2
3
Product Delivery Name | 4. Deploying Generic LLM within Internal Team
Delivery Description | Deploy a generic Large Language Model (LLM) within the internal team's environment, either the advanced analytics or another actuarial team. Specifically, we provide an interface or application that allows team members to interact with the deployed LLM. Additionally, enable the internal team to test, evaluate, and provide feedback on the LLM's performance, capabilities, and potential use cases.
What | 1) A fully functional and accessible LLM deployment within the internal team's environment (e.g., Azure cloud platform). 2) User interface or application for interacting with the deployed LLM. 3) Documentation and instructions for using the LLM interface. 4) Feedback mechanisms (e.g., feedback forms) for the internal team to provide their assessments and insights.
For Who | SRA Actuarial Senior Management Committee
Delivery Lead | Pavan Singh
By When | 0.5 Months Duration; Deadline: 1July 2024
Project Delivery Features
1
2
3
Product Delivery Name | 5. Deploying Generic LLM throughout Actuarial
Delivery Description | Based on the feedback and insights gathered from the internal team in Phase 4, this stage involves deploying the generic Large Language Model (LLM) across the entire actuarial department. The goal is to integrate the LLM into the department's workflows, processes, and tools, enabling actuaries to leverage its capabilities in their day-to-day operations
What | 1) Provide interface and LLM capability to actuarial department through an enterprise-wide deloyment. Ensuring secure and scalable deployment within Sanlam's infrastructure. Possibly provide robust access controls and user authentication mechanisms. 2) Comprehensive training materials (e.g., tutorials, documentation, video walkthroughs) provided for users to learn how to effectively use and interact with LLM, facillitating user uptake and usage. 4) Provide monitoring and evaluation tools to visualise the LLM's performance, adoption, and impact within the actuarial department. 5) Provide support channels (e.g., email address) for users to seek assistance, report issues, and provide feedback.
For Who | SRA Actuarial Senior Management Committee
Delivery Lead | Pavan Singh
By When | 1.5 Months Duration; Deadline: 15 August 2024
Project Delivery Features
1
2
3
Product Delivery Name | 6. Enhance Generic LLM with Sanlam Information
Delivery Description | The goal is to enhance the capabilities of the generic Large Language Model (LLM) by integrating it with Sanlam-specific information and knowledge sources. This will be achieved through the implementation of a Retrieval-Augmented Generation (RAG) approach, enabling the LLM to access and leverage Sanlam's proprietary data, documents, and domain-specific knowledge
What | 1) Provide a secure and scalable knowledge base storage solution consisting of identified relevant information sources (e.g., internal documents, reports, databases). 2) Delivery of a RAG implementation in Azure, by integrating the generic LLM with the Sanlam knowledge base. Enabling users to retrieve more informed and contextually relevant responses. 3) Deployment and release of RAG enhanced LLM within Sanlam Actuarial. Provisioning of necessary computing resources and infrastructure to support the RAG system's performance and scalability requirements ensured. 5) Provide a means for which comprehensive evaluation of the RAG-enhanced LLM's performance, accuracy, and relevance in Sanlam-specific scenarios can be monitored. And establishment of feedback mechanisms and user acceptance testing to gather insights and feedback from employees and stakeholders.
For Who | SRA Actuarial Senior Management Committee
Delivery Lead | Pavan Singh
By When | 1.5 Months Duration; Deadline: 1 October 2024
SRA Actuarial Project Sponsor Signature |  | Advanced Analytics Project Sponsor Signature
Date |  | Date

## Rough Deadlines
Task Name | Start (Date) | End (Date) | Duration (Days)
Explore & Upskill LLM Knowledge | 2024-02-01 | 2024-04-01 | 60
Securing Azure AI Sandbox | 2024-04-01 | 2024-05-15 | 44
Generic LLM Development on Azure AI Sandbox | 2024-05-15 | 2024-06-15 | 31
Deploying Generic LLM within Internal Team | 2024-06-15 | 2024-07-01 | 16
Deploying Generic LLM throughout Actuarial | 2024-07-01 | 2024-08-15 | 45
Enhance Generic LLM with Sanlam Information | 2024-08-15 | 2024-10-01 | 47