## Product_Roadmap
SanlamConnect Advisor Analytics Project Roadmap
| Created By | Business Unit | Business Unit Sponsor
| Luyanda Dhlamini (E1005314) | Advanced Analytics (Sanlam Retail Affluent Cluster) | Shabbeer Omar
1. Project Vision
Leverage the Data Science capability within Sanlam's Advanced Analytics team to create predictive models & performance dashboards (data assets ) that are used within Sanlam Connect's unit to improve effeciencies in Intermediary Advisor performance & retention.
2. Project Strategy
Empower managers & leaders throughout Sanlam's Product structures with data driven insights that enable them to: 1. Identify factors that predict individual advisor performance & likelihood of being retained as an advisor on a quarterly basis. 2. Use dashboards to monitor the progression of these predictive factors over time. 3. Use dashboards to obtain predictions of anticipated advisor performance & retention rates in upcoming periods. 4. Implement initiatives that will enhance advisor performance and increase advisor retention rates.
3. Project Stakeholders
| Person | Role(s) | Team / Unit ¦ Role
| Heinrich Punt | Project Sponsor - Sanlam Connect | SanlamConnect ¦General Manager: Connect Intermediaries
| Cornelius Vivier | Outcomes Customer | Sanlam Connect Finance ¦ Financial Manager
| Trisha Pillay | Project Support / SME - Sanlam Connect | Sanlam Connect Finance ¦ Regional Financial Manager
| Shabbeer Omar | Project Sponsor - Advanced Analytics | Advanced Analytics ¦ Head of Advanced Analytics
| Luyanda Dhlamini | Project Manager; Contributor - Data Scientist | Advanced Analytics ¦ Senior Data Scientist
| Siraj Dawood | Contributor - Data Scientist; Stakeholder Engagement | Advanced Analytics ¦ Data Scientist
| Jani Arangies | Contributor - Data Scientist | Advanced Analytics ¦ Data Scientist
| Pavan Singh | Contributor - Data Scientist | Advanced Analytics ¦ Associate Data Scientist
| Zahier Sedick | Contributor - Data Analyst | Governance & Regulatory ¦ Insights & Reporting Analyst
| Lizelle Hendricks | Delivery Lead; Scrum Master | Data Management ¦ Delivery Lead
| Dereck du Plessis | SME - MIS Data Warehouse | RA Actuarial: MIS Leading Analyst
| Other Sanlam Connect SMEs | SMEs; Knowledge Sharing; | SanlamConnect
** Trisha to re-invite other SanlamConnect members who are key stakeholders to the project
4. Project Deliveries
| Product Delivery Name | 1. Advisor Analytics Foundation
| Delivery Description | Precleaned datasets copied & transformed from the MIS datalake into the Cloudera datalake that are analytics ready, that allow Analysts from SanlamConnect & other departments to quickly access accurate, curated advisor specific data.
| What will be delivered: | 1. A cloudera dataset filtered to advisors, containing their demographic, input activity, output activity & income information. 2. A Confluence Wiki page that documents the advisor dataset's metadata & how the dataset is created. 3. Python scripts for reading, transforming & writing data from IBM DB2 to the Cloudera data lake.
| For Who: | SanlamConnect Internal Analysts; Other teams Sanlam Analytics Teams
| Delivery Lead: | Luyanda Dhlamini
| By When: | 2 Months Duration; Deadline: 1 April 2024 Extended Deadline: 30 May 2024
Project Delivery Features
1
2
3
| Product Delivery Name | 2. Advisor Rear View
| Delivery Description | An analysis of advisor retention & performance over the January 2021 to December 2023 period.
| What will be delivered: | 1. A powerpoint presentation summarising key findings extracted from advisor data over the period of analysis. These findings will include trends on advisor tenure, qualifications, demographics, earnings, new business generation. ( TO DO Sprint 3) Powerpoint for broader group AND screen recording 2. A Power Bi ( Tableau ) dashboard that allows end users to view annual trends in advisor demographics, retention & performance. This dashboard will be used by SanlamConnect managers - DONE |  | Sprint 3 Goal: Playback with minor touch-up and access to dashboard
| For Who: | SanlamConnect Finance Managers & Analysts; other analytics teams within Sanlam Group.
| Delivery Lead: | Zaahier Sedick & Siraj Rawood
| By When: | 2 Months Duration; Deadline: 1 June 2024 Extended Deadline:
Project Delivery Features
1
2
3
| Product Delivery Name | 3. Ingredients For Success
| Delivery Description | A statisitcal analysis of what quantifiable factors set apart "successful" advisors to their less successful counterparts.
| What: | 1. A powerpoint presentation detailing key findings of which factors set apart successful advisors to their counterparts. 2. Methods of Analysis templates/ playbooks that are used to identify attributes that are statistically significant for identyfying factors of success. 3. Contiously updated dashboards that track how the factors identified in above points are trending over time (updated monthly, using MIS data). |  | add in a 6month prediction( further expansion needed). We already have 3 month prediction. need to finalise 3 month model
| For Who: | SanlamConnect Regional & Unit Managers; Vesting Senior Managers
| Delivery Lead: | Jani Arangies
| By When: | 2 Months Duration; Deadline: 1 August 2024
Project Delivery Features
1
2
3
| Product Delivery Name | 4. Reasons For Leaving
| Delivery Description | What factors lead to advisor turnover (resignations & terminations).
| What: | 1. A powerpoint presentation showing the findings from analysis into factors that may indicate reasons for poor advisor retention. 2. Methods in which advisor retention can be analysed and factors to look out for reagrding advisor retention. 3. A dashboard that shows these factors in an interpretable way, highlighting possible at risk advisors. To be updated monthly and show trends over time.
| For Who: | SanlamConnect Regional & Unit Managers; Vesting Senior Managers; Connect HR & Academy
| Delivery Lead: | Siraj Rawood
| By When: | 2 Months Duration; Deadline: 1 October 2024
Project Delivery Features
1
2
3
| Product Delivery Name | 5. Advisor Crystal Ball
add in a 6 momth | Delivery Description | Creating models to predict advisor performance & probability to resign using Machine Learning. Existing advisor data will be used to train machine learning models that can infer advisor probability to terminate their contracts in an upcoming quarter as well as estimating advisor performance metrics (e.g. GemScore) over upcoming months.
| What: | 1. A powerpoint presentation describing the types of modes created as well as their intended use cases. 2. Machine learning models that are able to accurately predict advisor performance & likelyhood to terminate contracts with Sanlam. 3. Cloudera datasets with performance & retention predictions for each advisor that are updated periodically. 4. Dashboards that integrate the predictions in point 2 above with the most recent MIS statistics to forecast how advisors are likely to perform as well as how likely they are to churn.
| For Who: | SanlamConnect Regional & Unit Managers; Vesting Senior Managers
| Delivery Lead: | Pavan Singh & Siraj Rawood
| By When: | 2 Months Duration; Deadline: 1 December 2024
Project Delivery Features
1
2
3
| SanlamConnect Project Sponsor Signature |  | Advanced Analytics Project Sponsor Signature
| Date |  | Date

## Scraps
Product Delivery Name
Delivery Description
What:
For Who:
By Who:
By When:
Project Delivery Features
1
2
3